## Test Cases
Product Name |  | PriyoShop | TC Start Date | 2022-07-12 | TC Execution Start Date | 2022-07-12 | TEST CASE SUMMARY
Module Name |  | Test Cases for Registrassion Process | TC End Date | 2022-07-13 | TC Execution End Date | 2012-07-13 | PASS | 7
Epic |  |  | Test Case Developed By | Rased | Mobile (tested) | Yes | FAIL | 5
Developer Name (TL) |  | Q | Test Case Reviewed By | Md.Sabiul Islam | Performance (tested) | No | WARNING | 3
Test Executed by | [6 empty] | TOTAL | 15
Test Case ID/Name | Test Case Description | Precondition | Test Data | Step Description | Expected Result | Actual | Status | Remarks | comment
TC001 | Registration with preferable medium | Click on Register option from the "Account" option of the menu bar | Email option | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on email option-> fill all the boxes(Name,Email, Phone number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition "-> tap on the registr button | user should Register successfully | User can Register successfully | PASS
TC002 | Registration with preferable medium | Click on Register option from the "Account" option of the menu bar | Phone option | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Phone option-> fill all the boxes(Name,Email, Phone number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should Register successfully | User can Register successfully | PASS
TC003 | Registration with Email address | Click on Email from "Which medium do you prefer as user name?" option | Valid email address | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email option-> fill the email box with sara12@gmail.com -> keep the Phone number box empty->fill the other boxes(Name,Email, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should Register successfully | User can not Register successfully | WARNING |  | If the phone number is required then why the option(Which medium do you prefer as user name?) is given in the top section?
TC004 | Registration with Email address | Click on Email from "Which medium do you prefer as user name?" option | User name with special characters of an email | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email option-> fill the email box with @#$%@gmail.com -> fill all the boxes(Name,Email, Phone number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | FAIL
TC005 | Registration with Phone Number | Click on Phone from "Which medium do you prefer as user name?" option | Valid Phone number (Bangladesh) | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Phone option-> fill the phone Number box with 01721212121-> keep the Email box empty->fill the other boxes(Name, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should Register successfully | User can not Register successfully | WARNING |  | If the phone Email address is required then why the option(Which medium do you prefer as user name?) is given in the top section?
TC006 | Registration with Phone Number | Click on Phone from "Which medium do you prefer as user name?" option | Invalid Phone Number | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Phone option-> fill the phone Number box with 21212121->fill the other boxes(Name, Email Address, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can not Register successfully | PASS
TC007 | Verify the name | Click on Email or Phone option from "Which medium do you prefer as user name?" option | Special character | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email / Phone option-> fill the Name box with @%^&$# ->fill the other boxes( Email Address, Phone Number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | FAIL |  | Special Character can not be the name of a person
TC008 | Verify the name | Click on Email or Phone option from "Which medium do you prefer as user name?" option | Only Numeric value | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email / Phone option-> fill the Name box with 10876 ->fill the other boxes( Email Address, Phone Number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | FAIL |  | Numeric value can not be the name of a person
TC009 | Verify the name | Click on Email or Phone option from "Which medium do you prefer as user name?" option | Name with Small letter | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email / Phone option-> fill the Name box with tahsina ->fill the other boxes( Email Address, Phone Number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | WARNING |  | The first letter of a name should be in capital letter
TC010 | Verify the uername of email address | Click on Email option from "Which medium do you prefer as user name?" option | Capital letter in user name of an email | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email option-> fill the email box with MonikA@gmail.com -> fill all the boxes(Name,Email, Phone number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | FAIL |  | User name of an Email Address can not be in Capital letter
TC011 | Verify the domain of email address | Click on Email option from "Which medium do you prefer as user name?" option | Capital letter in domain of an email | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email option-> fill the email box with taniya@Gmail.CoM -> fill all the boxes(Name,Email, Phone number, Password, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should not Register successfully | User can Register successfully | FAIL |  | Domain of an email address can not be in Capital letter.
TC012 | Verify the Password | Fill all the boxes which are required | With 5 chatecters | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email / Phone option->fill the password box with 1qd12 -> fill all the boxes(Name,Email, Phone number, Confirm Password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | Pop up message should be shown | User can see the pop up message | PASS
TC013 | Verify the Confirm Password | Match the "Confirm password" with "Password" | With different chatecters in both Password and confirm password box | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email /Phone option->fill the password box with 1qd1o2t and fill the confirm password box with 06d1k2t -> fill all the boxes(Name,Email, Phone number, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | Pop up message should be shown | User can see the pop up message | PASS
TC014 | Verify the acceptence message from user side | Fill all the boxes which are required | Click ( the left side box of the message) | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email/phone option-> fill all the boxes(Name,Email, Phone number, Password, Confirm password, Street Address, District, Police Station)correctly ->don't tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | Pop up the message "Please accept the terms of service before the next step". | User can see the pop up message | PASS
TC015 | Verify the Register button | Fill all the boxes which are required and click on the "Acceptance masaage" | Click (the Register button) | goto PriyoShop app-> tap on menu bar-> tap on Account button-> tap on Register Now option-> tap on Email/phone option-> fill all the boxes(Name,Email, Phone number, Password, Confirm password, Street Address, District, Police Station)correctly -> tap on the message box of "I have read & accept terms & Condition"-> tap on the registr button | user should Register successfully | User can Register successfully | PASS

## Test Reports
Project Name: PriyoShop Sprint - 2 No. of Features: 1 No. of test Cases: 15 Total Bugs: 8
Test Case Run | [5 empty] | Component wise
Status | Count | %
Passed | 7 | 100% |  |  |  | Total Bugs | Backend | Android | Backoffice
Blocked | 0 | 0% |  |  |  | 8 | 0 | 8 | 0
Untested | 0 | 0%
Retest | 3 | 0%
Failed | 5 | 0%
| Severity | [5 empty] | Bug-Type
Component | Critical | Major | Minor | Low | Subtotal | Component | Functional | Visual | Content | Performance | Crash | Subtotal
Backend | 0 | 0 | 0 | 0 | 0 | Backend | 0 | 0 | 0 | 0 | 0 | 0
Android | 0 | 5 | 3 | 0 | 8 | Android | 0 | 0 | 0 | 0 | 0 | 0
Backoffice | 0 | 0 | 0 | 0 | 0 | Backoffice | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 5 | 3 | 0 |  | Total | 0 | 0 | 0 | 0 | 0 | 0
|  | Component vs Severity | [5 empty] | Component vs Bug-Type